## Sheet1
Feature | Tasks | Prioritisation | Due Date | Completed?
Loan Calculations | Build a function to initialise the loan details | HIGH | 2023-06-27 | 1
| Build a function to perform the calculation | HIGH | 2023-06-27 | 1
| Test the calculator with known results | Medium | 2023-06-28 | 1
| Wrap this into a class to be exported | Medium | 2023-06-28 | 1
User Input | Write psuedocode to understand what inputs will be required | HIGH | 2023-06-29 | 1